## Development effort
Development Effort Estimation
| The estimation will based on: | man-hour
1. Preparation
| Work Item | Total
| Framework and convention building | 0
| Business and technology training | 0
| Project Plan | 0
| Blueprint Preparation and approval from customer | 0
| Test Case | 6
| Project conventional and configuration | 2
| Total | 8
2. Implementation
| Work Item | Effort
|  | Requirement Analysis | System Design | Coding |  |  | Testing/ Bugs Fixing | Quantity | Total
|  |  |  | UI | Biz | Data
Requirement Analysis
| Business worflow analysis | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 4
| System requirement analysis | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 4
System Design
| Architecture Design | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 4
| Database Design | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 4
Android Coding & Testing
Konfirmand (Confirmation)
| - Home screen | 0 | 0 | 3 | 1 | 1 | 1 | 1 | 6
Regga en gudst jänst (register a church)
| - gudstjänst jag har varit med (Churchs I've been to) - 10 churchs | 0 | 0 | 2 | 1 | 1 | 0.8 | 1 | 4.8
| - Foto fran kyrkan (photo) | 0 | 0 | 4 | 1 | 2 | 1.4 | 1 | 8.4
Compatibility
| Devices with 480x854 screen resolution (Default supported) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Devices with 480x800 screen resolution (Default supported) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Devices with 320x480 screen resolution (Default supported) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Sub Total | 8 | 8 | 9 | 3 | 4 | 3.2
| Total | [7 empty] | 35.2
3. Delivery
| Work Item | Total | Note
| Test deployed application | 8
| UAT | 6 | Maximum 5 working days
| Packaging software | 0 | Pack the final app(s)
| Support to input sample data | 0
| Support to deploy on Customer device(s) | 0
| Total | 14
Summary
| Task | Scale | Total
| Development |  | 57.2
| Preparation |  | 8
| Implementation |  | 35.2
| Delivery |  | 14
| Warranty (30 days after UAT) |  | 2.86
| Fix lost bugs & issues | 5% | 2.86
| Project Management & SQA |  | 5.72
| Project Management | 5% | 2.86
| SQA | 5% | 2.86
| Total Project Effort |  | 65.78
Bac Ha Tech Ltd. Co. (IT-Software Consulting)
Floor 6th, Technosoft Building, Duy Tan Str., Cau Giay Dist., Hanoi, Vietnam
Tel: (844) 3795 1677 | Fax: (844) 3795 1676 | Email: info@bhtech.com.vn