## Phase 1 (Revised 2)
9Hug | 2014-08-13 | 2014-08-29
GOAL
[5 empty] | 2014-08-11 | 2014-08-12 | 2014-08-13 | 2014-08-14 | 2014-08-15 | 2014-08-16 | 2014-08-17 | 2014-08-18 | 2014-08-19 | 2014-08-20 | 2014-08-21 | 2014-08-22 | 2014-08-23 | 2014-08-24 | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | 2014-08-30 | 2014-08-31
[5 empty] | 2014-08-11 | 2014-08-12 | 2014-08-13 | 2014-08-14 | 2014-08-15 | 2014-08-16 | 2014-08-17 | 2014-08-18 | 2014-08-19 | 2014-08-20 | 2014-08-21 | 2014-08-22 | 2014-08-23 | 2014-08-24 | 2014-08-25 | 2014-08-26 | 2014-08-27 | 2014-08-28 | 2014-08-29 | 2014-08-30 | 2014-08-31
Item Description | Who? | Estimated (Man-hours) | Status | Remaining (Man-hours) | 0 | 0 | 8 | 8 | 4 | 0 | 0 | 8 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Features
Code organization | nghia_nong | 8 | Ongoing | 0 | 2014-08-13: 4; 2014-08-14: 4
Me screen UI &Biz | phuong_pham | 8 | Ongoing | 0 | 2014-08-13: 4; 2014-08-14: 4
Me Screen Services | nghia_nong | 4 | Planned | 0 | 2014-08-15: 4
Friends Screen UI & Biz | phuong_pham | 12 | Planned | 0 | 2014-08-18: 4; 2014-08-19: 4; 2014-08-20: 4
Friends Screen Services | nghia_nong | 4 | Planned | 0 | 2014-08-18: 4
Profile Screen UI & Biz | phuong_pham | 8 | Planned | 0 | 2014-08-21: 4; 2014-08-22: 4
Profile Screen Services | nghia_nong | 4 | Planned | 0 | 2014-08-19: 4
QR code Scanner Screen - Update UI | phuong_pham | 4 | Planned | 0 | 2014-08-15: 4
Capture Video Screen - Update UI | phuong_pham | 4 | Planned | 4
Capture Video Screen - Biz (rewrite record video) | nghia_nong | 4 | Planned | 0 | 2014-08-20: 4
Mix Video Screen - Update UI | phuong_pham | 4 | Planned | 4
Mix Video Screen - Update filters | nghia_nong | 4 | Planned | 0 | 2014-08-21: 4
Message List Screen Update UI & Biz | phuong_pham | 8 | Planned | 8
Message List Screen Services | nghia_nong | 4 | Planned | 0 | 2014-08-22: 4
Message Detail Screen - UI & Biz | phuong_pham | 8 | Planned | 8
Message Detail Screen - Services | nghia_nong | 8 | Planned | 8
Public Screen - UI & Biz | phuong_pham | 8 | Planned | 8
Public Screen - Services | nghia_nong | 4 | Planned | 4
Public Detail Screen - UI & Biz | phuong_pham | 8 | Planned | 8
Public Detail Screen - Services | nghia_nong | 4 | Planned | 4
UI Bugs fix | phuong_pham | 12 | Planned | 0 | 2014-08-25: 4; 2014-08-26: 4; 2014-08-27: 4
Services Bugs Fix | nghia_nong | 8 | Planned | 0 | 2014-08-25: 4; 2014-08-26: 4
Target |  | 140 |  | 0 | 132.6316 | 125.2632 | 117.8947 | 110.5263 | 103.1579 | 95.7895 | 88.4211 | 81.0526 | 73.6842 | 66.3158 | 58.9474 | 51.5789 | 44.2105 | 36.8421 | 29.4737 | 22.1053 | 14.7368 | 7.3684 | 3.908e-14 | 0 | 0